## Up to 100 kWp (4mo)
| Start Date = | 2026-08-12
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12
1 | Receipt of PO and Advance Order
2 | Customer Kick-Off Meeting
3 | Design Approval / Site Handover (whichever later)
4 | Submission & Approval of Design
5 | Placement of Orders on Vendors (Material Wise)
6 | Manufacturing & Dispatch of Materials
7 | Mobilization of Team at Site
8 | Installation & Test Charge
9 | Approvals
10 | Commercial Operation Date (COD)
11 | Site and Documentation Handover
| Start Date = | 2026-08-12 |  | Project End Date = | 2026-12-12

## 100-1000 kWp (5mo)
| Today = | 2026-08-12
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12 | 2027-01-12
1 | Receipt of PO and Advance Order
2 | Customer Kick-Off Meeting
3 | Design Approval / Site Handover (whichever later)
4 | Submission & Approval of Design
5 | Placement of Orders on Vendors (Material Wise)
6 | Manufacturing & Dispatch of Materials
7 | Mobilization of Team at Site
8 | Installation & Test Charge
9 | Approvals
10 | Commercial Operation Date (COD)
11 | Site and Documentation Handover
| Start Date = | 2026-09-12 |  |  | Project End Date = | 2027-01-12

## Above 1000 kWp (6mo)
| Today = | 2026-08-12
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12 | 2027-01-12 | 2027-02-12
1 | Receipt of PO and Advance Order
2 | Customer Kick-Off Meeting
3 | Design Approval / Site Handover (whichever later)
4 | Submission & Approval of Design
5 | Placement of Orders on Vendors (Material Wise)
6 | Manufacturing & Dispatch of Materials
7 | Mobilization of Team at Site
8 | Installation & Test Charge
9 | Approvals
10 | Commercial Operation Date (COD)
11 | Site and Documentation Handover
| Start Date = | 2026-09-12 |  |  | Project End Date = | 2027-02-12